Task List
Skullduggery
Greg Baker - Robert Koeninger
Advisor: Prof. Wilsey
Nov 18, 2009
Revised: Dec 4, 2009

Setup Source Control – November 8 – November 10
Source control for project documentation and source code should be set up ASAP

Setup Development Environment – November 8 – November 10
Development environments for relevant SDKs should be set up before we can investigate how to use them and what capabilities they have.

Research Phone SDK – November 13 – November 16
We need to research the SDK of the possible phones that we will use. Candidates are the iPhone, Android SDK, and Windows Mobile platforms.

Write User Requirements – November 8 – November 16
We need to write user requirements between November 8 and November 16. This is partly due to class assignments but also for direction during the project.

Write Use Cases/ Activity Diagrams - November 8 – November 20
Use Cases and Activity Diagrams will be written outlining what we need to do to have a successful project at the end of the year. These will be written after the User requirements have been hammered out.

Write Design Specification – November 20 – November 30
A formal design specification should be written after we write user requirements and activity diagrams. We will write a more formal design specification to show what progress we have and what we need to get done.

Research Encryption Methods – November 23 – December 1
We should know about which encryption methods we want to use before we start implementing the

Research Phone Communication Process – November 23 – December 1
We should know about how the cellular phones communicate before we can modify how they communicate.

Investigate Phone OS Source Code – December 13 – January 6
Knowing the specifics of how to use phone communication methods is vital to the success of the project.

Find/Develop Encryption Library – December 13 – January 6
Once we have selected an encryption method and know what aspects of the phone we're messing with, we can find or develop an encryption library that meets our requirements.

Write Principal Code – January 3 – March 7
The majority of the code will be written between January 3 and March 7.

Design Complete – January 18
This milestone shows the end of most of our design activities.

Acquire Phones – March 8
This milestone shows the latest date that we should have our cellular phones by.

Bug Fixing – March 8 – April 5
Bug fixing will take place after the majority of the code is written.

Code Writing Completed – March 8
The majority of the code should be finalized by March 8 in order to catch all the small bugs that might plague us during presentations.

Write Test Plan – Feb 14 – Feb 28
A more formal testing plan should be written before we test in emulated software.

Test in Emulation – Feb 28 – March 15
We should test in an emulated environment before the end of coding, and before we acquire phones and test on hardware.

Test on Hardware – March 3 – April 5
Hardware testing will take a long time, as it may be annoying and difficult to use.

Testing Completed – April 5
This milestone shows when we should have completed testing. It is ok to miss this deadline, but the bugs should start becoming features afterwards.

Product Completed – April 5
This milestone shows when we should be completed in order to have a “buffer” and to complete other assignments and properly complete the project report.

Project Report Completed – April 30
The final project report should be done by the end of April. If it isn't we will have time issues.

Prepare for Tech Expo – May 1 – May 5
Preparing for the tech expo up to a week in advance. This may be extended into April.

Tech Expo – May 6 - May 7
Present our project at the Tech Expo. These dates are estimates as we could not find them before.